## Sheet1
Week | <component> |  | Degree of Difficulty
2021-09-06 | Project Plan |  | Low
| Trello Board |  | Low
| Github Repo |  | Low
2021-09-13 | Create project scaffolding |  | low
| Replace scaffolding code with flask code |  | low
| Verify code runs localy |  | Medium
| Clone repo in Azure Cloud Shell |  | low
| Configure Cloud Shell environment |  | low
| Verify code runs in Cloud Shell |  | Medium
2021-09-20 | Configure Github actions |  | Medium
| Verify remote tests pass in Github actions UI |  | Low
| Create app service |  | Medium
| Test App Service |  | Low
| Create pipeline |  | Medium
| Test pipline |  | Medium
2021-09-27 | Demo video |  | Medium
| Complete documentation |  | Low
2021-10-04 | Submit project for review |  | Low
| Goals | Goals
Complete and submit project on time
Q4
Submit Project
Yearly
Update python packages
Ensure code and configuration is still valid